## Timeline
OD Sprint 2
No | Activity | Module | Page | PIC | Duration (Day) | Maindays (day) | Progress (%) |  | Start Date | End Date | Actual Date |  | Notes
[11 empty] | Start Date | End Date
1 | FCAB |  |  | All | 1 | 1 | 100% |  | TBD | TBD
2 | Gather Requirement & Assesment |  |  | TL, TC1 | 5 | 5 | 100% |  | TBD | TBD
3 | Design Implementation |  |  | TC2, TC3 | 10 | 20 | 100% |  | 2026-04-27 | 2026-05-11
4 | Development | Layout |  | TC4, TC5 | 5 | 5 | 100% | 100% | 2026-05-07 | 2026-05-19
|  | Master Data | List Request |  | 3 | 5 | 100% | 100% |  |  |  |  | asumsi with GET API
|  |  | Chart |  | 4 | 15 | 100%
|  |  | View Summary |  | 1 | 5 | 100% | [5 empty] | Replace Layout Master Data Baru
|  |  | Download Curret Data |  | 1 | 5 | 100%
|  |  | Upload Edit File |  | 1 | 5 | 100%
|  | Dashboard | Dashboard Detail Calculation | TC2, TC3 | 5 | 5 | 100% | 100% | 2026-05-18 | 2026-05-25
|  |  | List Request |  | 1 | 5 | 100% | [5 empty] | Enhancement Data Transition : Joining Table Job Function dan Capability (Competency)
|  |  | View Detail List Request |  | 1 |  | 100%
|  |  | View Summary |  | 1 | 4 | 100% | [5 empty] | Replace Layout Master Data Baru
|  | Request | Add Improvement Request |  | 2 | 7 | 100% | 100% |  |  |  |  | Butuh penjelasan terkait status flow
|  |  | Pop Up Confirmation |  | 1 | 2 | 100%
|  |  | Detail Progress |  | 1 | 4 | 100%
|  | Position | Edit Bagan (Edit Data) | TC4, TC5 | 5 | 8 | 100% | 100% | 2026-04-25 | 2026-06-09 |  |  | Enhancement Data Transition : Joining Table Job Function dan Capability (Competency) Masih menunggu konfirmasi terkait AI yang langsung di apply ke bagan
|  |  | Download Current Data |  | 1 | 4 | 100%
|  |  | Upload Edit File |  | 1 | 6 | 100%
|  |  | View Download supporting Document |  | 1 | 4 | 100%
|  |  | AI Integration |  | 5 | 12 | 100%
|  |  | Pop Up Submit |  | 1 | 3 | 100%
|  |  | Feedback |  | 3 | 3 | 100%
|  |  | pop Up Feedback |  | 1 | 5 | 100%
|  |  | Download & Upload Template |  | 1 | 3 | 100%
|  | PDM Dashboard | Acknowledge | TC2, TC3 | 3 | 5 | 100% | 100% | 2026-06-08 | 2026-06-15
|  |  | List Data |  | 2 | 3 | 100% | [5 empty] | Enhancement Data Transition : Joining Table Job Function dan Capability (Competency)
|  |  | Dashboard Detail PDM Calculation |  | 5 | 3 | 100%
|  | Competency Dashboard | Form Submit Competency |  | 1 | 7 | 100% | 100%
|  | Create Approval Document | Form Detail | TC4, TC5 | 1 | 10 | 100% | 100% | 2026-07-06 | 2026-07-20
|  |  | View Detail |  | 1 | 5 | 100%
|  |  | Download |  | 1 | 4 | 100%
|  |  | Download & Upload Template |  | 1 | 6 | 100%
|  | Update EBS | List Data |  | 2 | 5 | 100% | 92.86% |  |  |  |  | Ada Penambahan API View sikronisasi master data EBS ke OD -8 Juli 2026
|  |  | Edit Data List |  | 2 | 5 | 90%
|  |  | Edit Detail Form |  | 2 | 3 | 90%
|  |  | Download & Upload Template |  | 2 | 4 | 100%
|  |  | Upload EBS |  | 4 | 2 | 70% | [5 empty] | Masih ada API yang Error Job & Location
|  |  | Validate Data Proses |  | 2 | 6 | 100%
|  |  | Pop up confirmation |  | 2 | 2 | 100%
|  |  | Sinkronisasi master data EBS |  | 2 |  | 0%
|  | Email | PDM Dashboard | TC2, TC3 | 5 | 6 | 100% | 100% | 2026-06-25 | 2026-07-06
|  |  | Competency Dashboard |  | 3 | 6 | 100%
|  | Notification |  |  | 5 | 12 | 100% | 100%
|  | User Mapping |  |  | 3 | 5 | 100% | 100%
|  | Filtering dan listting Organisasi Rebahan |  | TC2, TC3 | 2 | 4 | 100% | 100% | 2026-07-17 | 2026-07-20 |  |  | Request API get All Data
5 | Create SRS |  |  | TC1 | 5 | 5 | 90% |  | 2026-07-08 | 2026-07-14
6 | Submit CRQ and SRS |  |  | TSel | 1 | 0 | 0% |  | 2026-07-21 | 2026-07-21
7 | Create UT and SIT |  |  | TC1, TL1 | 5 | 5 | 0% |  | 2026-07-14 | 2026-07-20
8 | Review TC |  |  | TSel, TC1, TL1 | 1 | 0 | 0% |  | 2026-07-21 | 2026-07-21
9 | UAT |  |  | All | 7 | 2 | 0% |  | 2026-07-21 | 2026-07-29
10 | NFT (If any) |  |  | All | 2 | 0 | 0% |  | 2026-07-30 | 2026-07-31
11 | Security Test |  |  | All | 10 | 4 | 0% |  | 2026-08-03 | 2026-08-14
12 | Production Preparation |  |  | All | 1 | 2 | 0% |  | 2026-08-18 | 2026-08-18
13 | RFS |  |  | All | 1 | 1 | 0% |  | 2026-08-19 | 2026-08-20
14 | FUT |  |  | All | 1 | 2 | 0% |  | 2026-08-21 | 2026-08-21
|  |  |  | Total Duration | 147 | 265

## Resource Refference
No | Member Name | Role | Email | Employee ID
1 | Indira | Business Analyst | sayyid@mii.co.id | EMP-SAYYID
2 | Dean | Developer Back-End | dean@mii.co.id | EMP-DEAN
3 | Fazri | Developer Back-End | fazri@mii.co.id | EMP-FAZRI
4 | Jansen | Developer Back-End | jansen@mii.co.id | EMP-JANSEN
5 | Tubagus | Developer Back-End | tubagus@mii.co.id | EMP-TUBAGUS
6 | Rayo | Technical Lead | rayo@mii.co.id | EMP-RAYO